December 13, 2009

LG

DRAFT

HFT PXL Ladder and Sector System Test with Development Plan for the PXL Readout Cable

The prototyping and development effort leading to ladder and detector level system testing for the STAR Heavy Flavor Tracker (HFT) Pixel (PXL) detector is in progress. There are four stages to the basic flow of this prototyping and development.

Stage 1 – Mechanical design and testing of prototype detector support structures. The analysis through numerical analysis, finite element modeling and computational fluid dynamics of mechanical designs for stability under the thermal, vibrational and mechanical loading and for heat transfer characteristics. This is followed by building mechanical mockups of the mechanical support components and extensive testing of the characteristics of these models with respect to the design calculations and simulations. This stage leads to the prototype design for the mechanical support and cooling systems.

Status – This stage is mostly complete. A presentation of the modeling and prototyping results was given by Howard Wieman at the STAR HFT CD-1 review and may be found here http://rnc.lbl.gov/hft/hardware/docs/cd1/PXL_CDR1_HW_25Oct2009_v13_no_backup.pptx

Stage 2 - The sensors and readout systems develop to the point of integrating them onto ladders. After the RDO functional design is verified with a full ladder data path test, the next step is to do a detailed design of the electronics components that are located on the ladder.  This involves the design of an electromechanical system, the readout cable, which supports the sensors and carries and buffers the signals to and from the ladder as well as providing latch-up protected power to the sensors. These systems are prototyped and tested.

Status – We have verified the RDO functional design with a full ladder data path test. The results may be found here: http://rnc.lbl.gov/hft/hardware/docs/LVDS/LVDS_test_report_1.pdf

A detailed description of the cable development effort may be found below.

Stage 3 – Ladders composed of fully functional sensors are now available to be mounted onto the support structures. This is done and ladder and sector level testing can now be performed. Full sectors composed of 4 ladders with each ladder containing 10 sensors are tested electrically and mechanically using all of the criteria and methods used in stages 1 and 2. The system is highly parallel with readout of individual ladders as the basic system unit.

Status – This stage of the development and testing is integrated into the prototype detector prototyping and ladder and sector production for the prototype. A section describing this effort may be found below.

Stage 4 – Sector production in which sectors with prototype sensors are integrated into a prototype detector. This prototype detector is then tested electrically and mechanically using all of the criteria and methods used in stages 1-3.

Status – The stage-4 development and testing is integrated into the prototype detector production and pre-installation testing. A section describing this effort may be found below.

## Stage -2 RDO Cable Development

The development of the Pixel detector readout cable is under way. The readout cable, which carries control signals, data signals and power to and from the ten sensors that make up a PXL ladder, is located between the thinned sensor and a carbon fiber stiffener plate. This readout cable is projected to be the single largest contributor to the radiation length of a ladder and thus we will make significant efforts to keep the X0 as low as possible. An initial design study based on limiting the number of layers in the low mass region of the cable and fitting the power and trace requirements to two sides of a flex PCB indicated that an aluminum conductor based cable could give a radiation length of less than 0.1 %. Using this design concept (http://rnc.lbl.gov/hft/hardware/docs/Phase1/cable_power_gnd_trace_optimization.doc ) as the baseline goal, we detail the development steps used to validate cable designs and sensor performance to reach this low X0 design. A presentation was given detailing this process at an IPHC collaboration meeting in June, 2009: (http://rnc.lbl.gov/hft/hardware/docs/iphc_2009_06/Flex_Cable_Development_LG.ppt)

The development of the cable to be used in the prototype Phase-1 based detector will be a four step process with four associated test beds. This prototype cable will serve as the basis for the design of the final sensor cable design. These steps along with the associated development and testing stages that lead to prototype Phase-1 and Mimosa-26 based cables as well as the additional steps leading to the final sensor pixel cable are listed below. The combination of these ladder cable development prototypes, which will be functionally identical to final detector ladders, and the prototype readout hardware, firmware and software required to read out and analyze the data from these cable test beds will form a ladder scale system test for the PXL detector.

System Test and Cable Development Sensors

We will use both the Phase-1 and Mimosa-26 sensors in the system test and cable development process. A comparison table of the relevant physical and operating parameters of each sensor is shown below.

| Parameter | Phase-1 | Mimosa-26 |
| --- | --- | --- |
| Clock Frequency | 160 MHz | 160 MHz |
| Readout Frequency | 160 MHz | 160 MHz |
| LVDS outputs / sensor | 4 | 2 |
| Pixel array size | 640 x 640 | 1152 x 576 |
| Pixel size | 30um x 30 um | 18.4um x 18.4um |
| Physical size | ~2cm x ~2cm | ~ 2cm x ~1cm |
| Zero suppression | No | Yes – 200 hits/memory array |

It is desirable to begin initial infrastructure and system testing with Phase-1 sensors since sensor characterization is much easier when testing sensors without zero suppression incorporated due to the limited hit memory space of Mimosa-26. The detailed characteristics and basic operation of each sensor may be found in the user manuals. The user manual for the Phase-1 sensor may be found here http://rnc.lbl.gov/hft/hardware/docs/Phase1/PH1-UserMan-20080916.pdf and Mimosa-26 sensor may be found here http://rnc.lbl.gov/hft/hardware/docs/Phase1/M26_UserManual.pdf.

At our current state of development we have all of the required firmware and software to allow for automated testing of ladders of Phase-1 sensors and will begin initial system testing with these sensors. As Mimosa-26 becomes available in quantity, we will modify the testing board layouts and verify our Phase-1 results with the Mimosa-26 sensors and finally with the final PXL sensors.

Infrastructure Test Stage

The goal of this test bed is to evaluate the general design of running 10 sensors on a ladder and find and test the working envelope of bypass capacitance and power supply and ground connection. In this test we will test extensively:

- LVDS clock multi-drop.

- JTAG daisy chain.

- Sensor and system bypass capacitor requirements.

- Power and ground routing and stiffness.

- Noise and cross-talk.

- General operation.

In order to accomplish this testing program, we will produce a large and highly configurable FR-4 based PCB. This testing board will allow for the operation of ten sensors in the running configuration, but with significant additional capabilities that will not be available on a ladder sized PCB. The envisioned board configuration capabilities include:

- Analog readout available from all sensors (RDO limit is one sensor or 8 channels at a time)

- Jumper selectable power source to each individual sensor.

- In series replaceable resistor for each sensor power supply (analog and digital)

- Removable board level capacitor bypassing.

- Removable individual sensor capacitor bypassing.

- Readout over 2m fine wire as per final ladders.

- Readout through the full HFT data path including Mass Termination Boards (MTB).

- All buffering and drivers use the same chips as the final ladder.

We will initially equip this test board with probe tested and characterized Phase-1 sensors. We will vary the operating parameters while monitoring each sensor on the ladder for deviation from it’s individually tested characteristics. It is expected that this testing will be comprehensive and result in an understood set of operational parameters and parameter envelope for sets of ten sensors operated in a ladder configuration. This will be necessary for the next phase of cable development.

Production Prototype in FR-4 with Cu Conductor

Taking the knowledge gained in the Infrastructure Test Phase, we now attempt to fit the readout cable traces into the required size of the ladder readout cable. The object of this test is to produce a real size FR-4 PCB with Cu conductor that contain the layout and signal paths that we will use for the final detector. In addition to the full functionality testing, this will allow for the full data path testing as well as optimizing the wire bonding and assembly development and testing. In addition, all testing stages from this stage on will be tested with the carbon fiber stiffener plate in place. This production prototype is expected to have the following attributes:

- Correct size and the same layout geometry as the final cable.

- The testing of this cable is via digital output only. All other testing functionality removed.

- Prototype of final termination, JTAG daisy chain and capacitive bypassing scheme.

- All buffering and drivers use the same chips as the final ladder.

- Power provided from MTBs.

- Readout over 2m fine wire as per final ladders.

- We will attempt to have the thickness of the Cu layer mimic the final cable to give the correct power and ground impedances.

The testing of this cable is via digital output only. General function will be tested as well as discriminator transfer function widths and noise as compared to the probe test results from the sensor prior to their loading onto the cable. It is anticipated that this design may take multiple iterations to troubleshoot and optimize.

Production Prototype in Kapton with Cu conductor

This cable is a pre-production cable in Kapton with Cu traces and is the direct translation of the previous stage cable into a Kapton flex cable design. This will involve some reshaping of via entries and other automated kapton flex design translations from standard FR-4 PCB design. The attributes and testing plan for this stage are as above in the FR-4 version. It is expected that we will be using this cable extensively in the production prototyping process.

Production (Final PXL) Cable in Kapton with Cu Conductor

After the successful development of the Phase-1 based prototype cable, we expect the transition to the PXL final sensor cable design to be relatively simple. The number of digital differential output pairs has now decreased by half. The power requirements have only modestly increased. We will examine the operation envelope in the individual testing phase and compare it to the Phase-1 sensor. The final PXL sensor shares all of the attributes of the Phase-1 sensor but has additional on-chip zero-suppression. The readout speed remains the same at 160 MHz. The cable development for the final PXL sensor will follow the same path as the last two phases of the Phase-1 development.

Production (Final PXL) Cable in Kapton with Al Conductor

As before, after the successful implementation in Kapton with Cu conductor, we will move to Al conductor based fabrication. It is desired that we make an early start on pre-production designs and iterate with the manufacturer so that any production difficulties encountered in the initial manufacturing can be understood and overcome.

System Test Firmware and Software Development

The development paths of the software and firmware parallel the development path of the hardware for the sensor ladder cable development and system testing. In the initial infrastructure testing, we will begin with our existing functional individual sensor readout firmware and software. We will then extend the readout firmware and software (from one to multiple parallel streams) to full ladders of 10 sensors using the infrastructure test bed to validate the firmware/software development effort. A successful completion of the initial infrastructure test requires having working ladder readout firmware and software. Firmware and software changes to allow for reading different sensor output formats due to the incorporation of zero-suppression on post Phase-1 generations of sensors will be built in natively to the software and firmware design and implemented as a pre-processing firmware module that implements the IPHC zero-suppression scheme. This pre-processing module will be used when reading out Phase-1 based ladders. This allows us to keep all downstream firmware and software the same for all currently envisioned generations of sensors.

Schedule, Effort and Deliverables

This development effort is scheduled for the current FY10 year and is underway. The estimated effort can be found in the HFT Pixel cost estimation sheets presented in the HFT CD-1 review. The relevant WBS items are presented below:

1.2.2.3.1	Infrastructure Test Cable

1.2.2.3.2	Prototype Ladder Cable (FR-4)

1.2.2.3.3	Ladder Cable (Kapton with Cu conductor)

1.2.2.5.1	Firmware and software (PH-1 readout) fy10

The total effort summed over the above WBS items is shown below:

| Material | Tech (hr) | Postdoc (hr) | Engineer (hr) | Eng. Cont (hr) |
| --- | --- | --- | --- | --- |
| 70 k$ | 512 | 1324 | 288 | 1830 |

The final deliverable from this prototyping effort is a working system test-bed consisting of

- Written report detailing testing described above and indicating the expected operating envelope of ladders of sensors.

- Working infrastructure test board with 10 working sensors.*

- Working production prototype test board in FR4 with 10 working sensors.*

- Working production prototype test board in Kapton with 10 working sensors.*

- Prototype firmware and software for reading out and analyzing data from 10 sensor ladders.

- RDO hardware including prototype Mass Termination Boards (MTB) and RDO motherboards with all cabling required for readout.

* having 10 working sensors/ladder is contingent on successful development of probe testing to allow us to select only working sensors to mount to ladders.

## Stage – 3 Ladder and Sector Testing

Stage 3 concentrates on the full testing of sectors for electrical and mechanical characteristics. The full RDO system hardware, firmware and software for reading out ladders and sectors of sensors were developed in stage-2. The stage-3 phase includes the testing of ladders composed of fully functional sensors mounted onto the support structures. These functioning sectors will be tested using the same testing procedures and methods as used in the stage – 1 mechanical testing;

- Sensor performance in sector configuration.

- Vibrational stability

- Positional stability

- Air cooling performance with operating sensors of a sector level

- Deformation measurement using TV Holography distortion measuring equipment.

Schedule and Effort

The tasks associated with stage-3 prototype ladder production are located in WBS 1.2.2.4 PXL Prototype Ladder Assembly.  This task is scheduled for FY12. The total effort summed over this task is shown below;

| Material | Tech (hr) | Postdoc (hr) | Engineer (hr) | Eng. Cont (hr) |
| --- | --- | --- | --- | --- |
| 78 k$ | 1168 | 546 | 64 | 632 |

## Stage – 4 Prototype Testing

In stage – 4 the sectors produced with prototype sensors are integrated into a prototype detector. This prototype detector is then tested electrically and mechanically using all of the criteria and methods used in stages 1-3. In addition to the tests listed in stage -3 we will be performing the following system level tests;

- Overall detector position stability

- Sector to sector position stability

- Air cooling performance with operating sensors of a detector level

- Sensor performance at the detector level

- Insertion and removal mechanics with a full detector.

- Ancillary support mechanics and electronics.

- Grounding and noise characteristics.

Schedule and Effort

The tasks associated with stage-4 prototype sector production are folded into the in WBS 1.2.2.6 PXL Sensor Ladder Production.  This task is scheduled for FY13.